## Sheet1
Date | Task | Estimate | Start | End | Breaks/Away | Total Measured Time | Error % (Accum.) | Adjusted Estimate | Description/Notes | For full description of task/issue/response go to Learning Journal
2022-08-02 | Settings Menu Begin | 2 | 9:35 | 15:30 | 2:52 | 3.05 | 152.5% | 3.05 | Full menu system, with settings and multi scene transition, and pause
2022-08-02 | Pause, Main Menu, Exit System | 1.5 | 16:00 | 17:20 | 0:25 | 0.91667 | 113.3% | 1.7 | Continuation of Menu system
15/02/22 | Line Renderer Waypoint | 3 | 9:15 | 10:33 | 0:16 | 1.0333 | 76.92% | 2.3077 | Line renderer, changing from Point A to Point B
22/02/22 | Image Scroll Rect | 2 | 9:10 | 9:34 | 0:00 | 0.4 | 63.53% | 1.2706 | Using UI system.
22/02/22 | Scroll Rect Toggle | 0.5 | 9:51 | 10:06 | 0:00 | 0.25 | 37.14% | 0.18571 | Additional toggle control for Menu system
2022-04-03 | Multiple Choice Quiz System | 2.5 | 14:50 | 17:44 | 0:35 | 2.3167 | 69.28% | 1.7319 | Multiple choice system with in-editor controls
14/03/22 | Game Scene Setup | 0.5 | 14:30 | 14:50 | 0:00 | 0.33333 | 69.17% | 0.34583 | Unity Project Setup, Packages ready to implement
14/03/22 | Package Implementation 1 | 2.5 | 14:50 | 16:38 | 0:10 | 1.6333 | 68.51% | 1.7126 | First two setup and functioning in scene
29/03/22 | Package Implementation 2 | 1.5 | 15:35 | 18:44 | 0:20 | 2.8167 | 79.69% | 1.1953 | Add last two packages. Prepare to combine into gameplay experience.
2022-04-04 | Game Refinement | 3 | 11:10 | 14:56 | 0:40 | 3.1 | 83.42% | 2.5026 | Normalising all Fonts, ensuring functioning with questions and tested