## Sheet1
Task | Date | Baseline estimate (hours) | Start | End | Interruptions | Measured time (hours) | Error % | Adjusted estimate
Researching Player Movement/implementing movement | 2022-02-04 | 1 | 11:00 | 12:00 | 0:15 | 0:45 | 0:15 | 0:15
Researching Enemy AI/implementing | 2022-02-05 | 2 | 9:00 | 11:00 | 0:30 | 1:30 | 0:30 | 1:00
Health and Damage research/implementing | 2022-02-09 | 2 | 9:00 | 13:00 | 0:45 | 2:15 | 0:15 | 0:30
New enemy types/behaviours | 2022-02-12 | 2 | 10:00 | 12:00 | 0:30 | 1:30 | 0:30 | 1:00
New enemy type/behaviour + enemy health/damage | 2022-02-15 | 2 | 9:00 | 11:00 | 0:30 | 1:30 | 0:30 | 1:00
Minimap | 2022-02-22 | 1 | 9:00 | 10:00 | 0:00 | 1:00 | 0:00 | 0:00
Score system and pickups | 2022-02-28 | 4 | 9:00 | 13:00 | 0:30 | 3:30 | 0:30 | 2:00
Menus | 2022-03-08 | 2 | 10:00 | 13:00 | 0:30 | 2:30 | 0:30 | 1:00
Tweaking enemy AI/movement (rotate to player transform) | 2022-03-10 | 2 | 9:00 | 11:00 | 0:15 | 1:45 | 0:15 | 0:30
Adjusting enemy projectiles (trigger on player collision) | 2022-03-14 | 2 | 10:00 | 13:00 | 0:30 | 2:30 | 0:30 | 1:00
Fixed menus and player win status | 2022-03-18 | 2 | 9:00 | 11:00 | 0:30 | 1:30 | 0:30 | 1:00
Exporting packages | 2022-03-25 | 2 | 9:00 | 10:00 | 0:00 | 1:00 | 0:00 | 0:00
Movement system FPS parkour | 2022-04-01 | 2 | 9:00 | 13:00 | 0:45 | 3:15 | 1:15 | 2:30
Researching other movement systems | 2022-04-08 | 2 | 10:00 | 12:00 | 0:00 | 2:00 | 0:00 | 0:00
Wall run/jump | 2022-04-15 | 2 | 9:00 | 11:30 | 0:30 | 2:00 | 0:00 | 0:00
Moving platforms | 2022-04-22 | 2 | 9:00 | 13:00 | 0:45 | 3:15 | 1:15 | 2:30
Implementing new FPS and Third person movement systems | 2022-04-29 | 3 | 9:00 | 1:00 | 0:30 | 2:30 | 0:30 | 1:30
Packaging programming CW2 | 2022-05-04 | 2 | 10:00 | 12:00 | 0:00 | 2:00 | 0:00 | 0:00