## Sheet1
Task | Date | Baseline estimate (hours) | Start | End | Interruption | Measured time (hours) | Error % | Adjusted estimate | Yotube tutorial link | Assets
A moving platform | 2022-02-08 | 1 | 9:53 | 12:02 |  |  |  |  | https://www.youtube.com/watch?v=rO19dA2jksk |  | null
Scale object | 2022-02-22 | 0.5 | 9:29 | 10:30 | 0:08 | 0.88333 | 176.7% | 0.88333 | none
card manager(collection list) | 2022-03-08 | 2 | 9:37 |  | 12:01 |  |  |  | https://www.youtube.com/watch?v=mhwGQ9XRBD8 | Assets from totorial video | not completed
moving platform 2(left to right) | 2022-03-15 | 1 | 10:20 | 11:14 | 0:02 | 0.86667 | 116.7% | 1.1667
moving platform (up/down) | 2022-03-15 | 0.16 | 11:52 | 12:10 |  | 0.3 | 123.5% | 0.19759
falling platform(moves hor/vert) | 2022-03-22 | 1 | 10:00 | 12:21 | 0:05 | 2.2667 | 162.3%
disappearing platform | 2022-03-29 | 0.5 | 10:05 | 11:35 | 0:20 | 1.1667 | 98.1% | 0.49048 | https://www.youtube.com/watch?v=Ozpv69HWrcw