## Sheet1
| OliverMota | Task Description | Est. Time | Start Date | Start Time | Finsh Date | Finish Time | Total Time | Interruptions/Breaks | Measured Time | Error% | Adjusted estimate
1 | EndlessCorridor | Create a looping corridor which the player can only escape by walking backwards | 4:00 | 2022-08-02 | 9:00 | 15/02/2022 | 10:10 | 4hrs 10mins | 45 Mins | 3:25 | 85.42% | 3:25
2 | Shop System | Create a shop layout where the player can spend money and choose items. | 3:00 | 15/02/2022 | 11:00 | 22/02/2022 | 10:00 | 2hrs | 20 Mins | 1:40 | 72.62% | 2:11
3 | Highlight/Raycast | When the player looks at an object it highlights to show its selected | 1:30 | 22/02/2022 | 10:20 | 22/02/2022 | 11:16 | 55 mins | 25 mins | 0:30 | 65.69% | 0:59
4 | CodeLock | 0-9 CodeLock, the code (set in unity) needs to be input to activate something | 2:00 | 2022-08-03 | 9:00 | 2022-08-03 | 11:45 | 1hr 45mins | 20 mins | 1:25 | 66.67% | 1:20