## Sheet1
Date | Start | End | Break | Estimated Time | Time Spent | Description | Error% | Adjusted Estimated
2022-02-08 | 9:30 | 9:45 |  | 0:10 | 0:15 | Working on the first of the four packages | 66.67% | 0:07
2022-02-08 | 9:45 | 10:45 | 0:10 | 0:30 | 0:50 | Watching tutorials on how to make an health system | 60% | 0:18
2022-02-08 | 10:45 | 11:00 |  | 0:30 | 0:15 | Designing the health system UI | 200% | 1:00
2022-02-08 | 11:00 | 12:00 | 0:10 | 1:00 | 0:50 | Coding health system | 120% | 1:12
2022-02-12 | 10:00 | 12:00 | 0:20 | 1:30 | 1:40 | Previous coding health system did not work so I am going to start coding a new one | 90% | 1:21
2022-02-15 | 9:30 | 10:30 |  | 1:00 | 1:00 | Watching tutorials on how to make damage by clicking a button | 100% | 1:00
2022-02-15 | 10:45 | 11:45 |  | 1:00 | 1:00 | Impementing the ability to click a button and deal damage to the health | 100% | 1:00
2022-02-18 | 14:00 | 16:00 | 0:20 | 2:00 | 1:40 | Started having ideas for RCR and starting the coding tomorrow | 120% | 2:24
2022-02-19 | 14:00 | 16:00 | 0:20 | 2:30 | 1:40 | Watching tutorials and started coding RCR | 150% | 3:45
2022-02-22 | 9:30 | 10:30 |  | 0:45 | 1:00 | Ideas for the second package | 75% | 0:34
2022-02-22 | 10:45 | 11:45 |  | 1:30 | 1:00 | I have decided to implement an enemy package which will be used with the health package to deal damage to the player | 150% | 2:15
2022-02-26 | 17:00 | 19:00 | 0:30 | 1:30 | 1:30 | I have been continuing coding RCR and I'm now working on the movement | 100% | 1:30
2022-03-03 | 15:00 | 17:00 | 0:15 | 2:00 | 1:45 | Today I will be coding the movement for RCR and I'm asking help from Paul as I'm unable to code a swipe control | 114.3% | 2:17
2022-03-03 | 17:00 | 18:00 |  | 1:00 | 1:00 | Paul has been kind enough to send me a swipe control script that works perfectly but I'll make a few changes | 100% | 1:00
2022-03-08 | 9:30 | 10:30 |  | 1:00 | 1:00 | I have had many problems coding the player to get damage when approaching an enemy and I'll now ask David for help | 100% | 1:00
2022-03-08 | 10:45 | 11:45 |  | 1:30 | 1:00 | David has helped me to get the player to be damaged when approaching an enemy, although I still want to implement other thing in this package | 150% | 2:15
2022-03-12 | 12:00 | 14:00 | 0:15 | 2:00 | 1:45 | Coding for RCR | 114.3% | 2:17
2022-03-15 | 9:30 | 10:30 |  | 0:30 | 1:00 | Watching tutorials of a system to make enemies walk in random points | 50% | 0:15
2022-03-15 | 10:45 | 11:45 |  | 1:30 | 1:00 | Coding was not working so I'll ask David for help next week | 150% | 2:15
2022-03-22 | 9:30 | 10:30 |  | 2:00 | 1:00 | Fixing problems with the coding | 200% | 4:00
2022-03-22 | 10:45 | 11:45 |  | 0:45 | 1:00 | David has helped me to code the enemies to randomly move | 75% | 0:34
2022-03-25 | 14:00 | 16:30 | 0:30 | 1:30 | 2:00 | Continuing to code for RCR | 75% | 1:08
2022-03-29 | 9:30 | 10:30 |  | 0:30 | 1:00 | Watching tutorials on how to code a Main Menu | 50% | 0:15
2022-03-29 | 10:45 | 11:45 |  | 1:00 | 1:00 | Started the menu coding but still to finish | 100% | 1:00
2022-04-11 | 15:00 | 18:00 | 0:30 | 1:30 | 2:30 | Coding for RCR | 60% | 0:54
2022-04-14 | 16:00 | 18:00 | 0:15 | 1:00 | 1:45 | Finished coding the Main Menu | 57.14% | 0:34
2022-04-19 | 12:00 | 15:00 | 0:20 | 1:30 | 2:40 | Watching tutorials on how to code a Pause Menu and had a few issues and didn't finish coding | 56.25% | 0:51
2022-04-22 | 15:00 | 17:00 | 0:30 | 2:00 | 1:30 | RCR coding | 133.3% | 2:40
2022-04-26 | 17:00 | 19:00 | 0:20 | 1:00 | 1:40 | I have finished to code the Pause Menu | 60% | 0:36
2022-05-03 | 9:15 | 10:15 |  | 1:00 | 1:00 | Watching tutorials on how to make a respawn system | 100% | 1:00
2022-05-03 | 10:15 | 11:15 |  | 1:00 | 1:00 | Coding respawn system | 100% | 1:00
2022-05-03 | 11:00 | 14:00 | 0:30 | 1:30 | 2:30 | Implementing all the packages together to make the game and bug fixing | 60% | 0:54